## Sheet1
Belize National HIV/STI/VH and TB Implementation Plan 2021-2025
PRIORITY STRATEGY FOR PREVENTION | Priority Intervention | Specific Activities | Timelines |  |  |  |  | Lead Agency | Collaborating agencies and partners
|  |  | 2021 | 2022 | 2023 | 2025 | 2025
STRATEGIC PRIORITY AREA 1: INFORMATION FOR TARGETED RESPONSE
Increase the use the BHIS | Scale up the use of the BHIS to the private health sector and CSOs | 1. Provide computer hardware and IT infrastructure of the effcetive functioning of the BHIS
2. Conduct training and ongoing supervision on the use of the BHIS
3. Conduct training on site specific data analysis for service delivery improvement
Generate more granular , high quality data for action | Strenghten and Scale up the use of BHIS | 1. Review of the BHIS to ensure that adequate data is captured to cover reporting needs for HIV/STI/VH and TB
| Develop continuum of care cascades | 1. Develop real time prevention cascades for HIV/STI/VH and TB
2. Develop real time prevention cascades for HIV/STI/VH and TB for key populations
2. Develop real time continuum of care cascades for HIV/STI/VH and TB
2. Develop real time continuum of care cascades for HIV/STI/VH and TB for key population
Ensure data protection and client and community safety | Strenghten data protection systems for collecting, storing and reporting data | 1. Develop and adapt data protection policy
2. Develop update and review normative guidance on data protection
3. Train data collector, users and health care worker on data confidentiality in collecting, storing and sharing of data
Access the national burden of HIV/STI/VH and TB |  | 1. Generate prevalence data for the all populatons and subpopulations: MSM, SW, Blood donors, pregnant mothers
2. Generate data on the prevalence, health consequences and impact of co-infections and co morbidities
Strenghten Laboratory Surveillance for HIV/STI and TB to monitor for gonococcal resistance, HIV drug resistance and MDR TB resistance | Strenghten laboratory quality assurance | 1. Implement and monitory laboratory quality assurance polcy
| Conduct HIV Drug resistance survey | 1. Establish TWG to provide leadership and oversight to the implementation of the HIV Drug Resistance Survey
2. Develop protocol for HIV Drug Resistance Survey
3. Conduct taining for documentation and data collection
4. Conduct training for blood collection and transportation
5. Conduct ongoing monitoring and supervision of implementation of the survey
6. Conduct data entry training
7. Conduct data analysis
8. Develop report that includes recommendations for changes in HIV treatment
9. Develop a dissemination plan to share findings of the survey.
10. Liaise with the Treatment Working Group to discuss findings and recommendation to guide changes to HIV treatment guidelines
| Build local capacity to conduct HIV drug resitance survey | 11. Conduct ongoing mentoring and capacity building for survey staff to conduct HIV Drug Resistance Survey
| Strenghten existing surveillance systems for the monitoring of HIV drug resistance, gonococcal resistance and MDR TB | 1. Conduct review of the laboratoy capacity to conduct ongoing HIV drug resistance, gonococcal resitance and MDR TB resistance.
2. Implement recommendation of laboratory capacity review to stregnthen diagnosis capabilities and monitoring for drug resistance
Establish second generation surveillance |  | 1. Conduct a review of the surveillance system to understand the gaps and needs to ensure second generation surveillance
2. Update surveillance systems to facilitate second generation sirveillance- review of surveillance manual, roles and responsibilities of persons in surveillance, data collection systems and tools
Data driven decision making | Annual Review and national target setting processes | 1. Generate integrated annual data driven programme reports on HIV/STI/VH and TB
2. Conduct annual data sharing forum with national stakeholders and develop recommendations to strenghten policy and programming
3. Conduct annual target review and target setting process
Enhance governance and accountablity and data sharing | Establish Governance Mechanism for data accountability | 1. Establish Broad Based Strategic Information Technical Working
2. Convene quartley meetings of the Siworking group
| Establish Data dash boards that is accessible to policy makers, programme planners and implemters, donors and funders, technical agencies | 2. Develop and maintain data dash boards with current on prevalence, indicence, impact and coverage outcomes as well as treatment cascades
| Strenghten functional roles and responsibilities for data collection, analysis and reporting | 3 Conduct a review of the surveillance systems for collecting, analysis and reporting for comprehensive data collection for HIV/STI/VH and TB
4. Review and update surveillance manual, standard operating procudures, guidelines and tools for data collection, analysis and reporting, including clear definition of roles and responsibilities
5. Conduct estimates and submit timely and comprehensive report to the UNAIDS Global AID Monitoirng Process, PAHO Universal access
Enable and Promote Research |  | 1. Develop and implement a research agenda
2. Collaborate with teritary institutions to implement research
3. Build capacity to conduct research including protocol development, research ethics, data analysis
4. Train and establish a cadre of principal investigators
5. Build capacity on data analysis- qualitative and quantitative
6. Support the strenghtening of national and local IRB processes
STRATEGIC DIRECTION 2 : SERVICE DELIVERY FOR IMPACT
PREVENTION
Strengthen governance, accountability and national planning for HIV/STI/VH and TB | Strenghten coordination for the delivery of HIV/STI/VH and TB prevention services | 1. Establish National Prevention Technical working group and conduct quarterly meetings for coordination of prevention services
2. Conduct quarterly quality assurance/ oversights to public, private and CSO sites delivering HIV/STI/VH and TB prevention services.
3. Conduct annual prevention review- identify gaps and opportunities, revise prevention programming and reset prevention targets
3. Liaise with Treatment and STI working groups to comprehensively address issues along the prevention and treatment and care continuum
Deliver High Impact Combination Preventon on HIV/STI/VH and TB | Define and regularly review and update the package of prevention services for Key Populations | 1. Define, review and update annually, package of prevention services for HIV/STI/VH and TB focusing on key populations
2. Develop guidelines of the delivery of prevention services for KPs
3. Identify and build capacity of CSOs and Private Sector to deliver the package of prevention services of KPs
4. Develop MoU with CSO and Private Sector to deliver the package of prevention services to KPs.
5. Conduct quarterly quality and monitoring and reporting oversight visits to CSOs and Private Sector
6. Conduct quartely KP programme review with KPs, CSO, Private sector and Health Care workers
Enhance Behaviour Change Communication for risk reduction | Increase access to risk reduction counselling, messaging and eduction | 1. Develop and update Intergated Behaviour Change Communication Plan for HIV/STI/VH and TB
2. Implement Behaviour Change Communicaton Plan
3. Training Health Care Workers- peer educators, counsellors, social workers on education and counselling risk reduction and behavior change for HIV/STI/VH and TB including condom negiotation use.
4. Monitor the effectiveness and impact of Behaviour Change Communication
Intensify condom programming | Increase access to male and female condoms and lubricants | 1. Review, update and implement national condom strategy
1. Develop/ Review and implement condom marketing strategy for increased condom uptake and use
2. Train peer educators and health care staff to educate KPs to conduct education o on the correct use and consistent of condoms
3. Build capacity and train health care and other staff on quantificaton of male and female condoms
4. Provide condoms and Lubricants to CSO for KPs
Ensure all Blood and Blood products are safe for transfusion | Screen all blood and blood products are screen for HIV/STI/ VH based on national protocols | 1. Screen all blood and blood products for HIV, STI, VH and other infectious markers.
2. Conduct ongoing quality assurance and quality control for blood screening for HIV/STI/VH and other infectiousmarkers
4.Conduct regular quanitification of reagents, test kits and consumables for screening of blood and blood products
3. Produce annual blood banking report that includes the prevalence of HIV/STI/VH among blood donors.
Reach, counsel and test all contacts of persons with HIV/STI/VH and TB | Conduct contact tracing for all contacts with HIV/STI/VH and TB | 1. Develop and update outreach manual/ contact tracing manual for outreach to contacts of HIV/STI/VH and TB
2. Train and Retrain Health Care and community workers on protocols for contact tracing including client confidentiality
3. Update all tools for contact tracing such as client intake, daily log, monthly reports and others
4. Conduct regular monitoing of the outcomes of contact tracing including succsess rate in contact tracing
Scale up quality assured HIV/STI/VH and TB testing using new approaches with better yield to reach the most at risk populations | Scale up HIV testing to reach for better yeild | 1. Review and update testing policy, strategy, guidelines and protocols to include new testing appraoches- HIV self testing, routine testing in some situation, PITC, and community based testing and the role of lay testors in expanding testing services
2. Train and retrain testing staff ( public and private health sectors and CSOs) on HIV/STI/TB testing protocols including the 5 Cs of HIV testing- consent, confidentiality, counselling, correct test results and connections to care, treatment and prevention services.
3. Develop and implement communication to strategies to create demand for testing among men.
| Diversify testing approaches to include newer and more effective modalities such as HIV self-testing and community- based testing, provider- initiated testing that integrates HIV/STI/VH and TB testing | 1. Develop a HIV self- testing policy
2. Collaborate with CSO such as the Belize Family Life Association and the CSO Hub to pilot HIV self-testing for KPS.
3. Conduct an evaluation of the HIV Self Testing Pilot.
4. Collaborate with CSO and the private sector expand HIV self-testing
5. Train and retrain CSOs on HIV self-testing
6. Develop tools, IEC materials for KPs to understand the self-testing process/ steps in self testing.
7. Develop reporting mechanisms and tools for reporting on self testing to the national programme
8. Support CSOs for community-based testing
| Ensure quality assured testing | 1. Review and update quality protocols
2. Implement and monitor quality protocols
3. Train laboratory staff and testing and field staff on quality protocols
4. Develop work-aids for laboratory and testing staff on quality protocols
Ensure access to Hepatitis B and HPV vaccinations | Scale up access to Hepatits B vaccine and HPV vaccines | 1. Review and update protocols for to expand access to Heptatitis B vaccines to include all unvaccinated children, adults are high risk for infections- MSM andTG
2. Develop and implement communication strategy to increase the uptake of Hepatits B and HPV vaccines
3. Train public and private health care workers on counselling and client education on Hepatitis B and HPV vaccines
4. Develop IEC materials for HPV and Hepatitis B vaccines
5. Intergate Hepatitis B and HPV vaccines into Primary Health Care.
6. Engage and provide support to CSO and the private health sector to deliver Hepatits B and HPV vaccines as part of their essential package of services.
Prevent HIV infection with Pre-Exposure Prophylaxis | Develop and Implement a HIV Pre-Exposure Prophylaxis programme | 1. Conduct costing analysis for HIV PrEP to understand the cost of PrEP per patient, the impact in averting new HIV infections and the associated long term cost savings
2. Develop and adopt PrEP policy.
3. Develop Guidelines, protocols and normative guidance for Pre-exposure prophylaxis. Integrate STI and VH screening and referral.
4. Develop and implement MoU with the Private Health Sector and CSOs to deliver PrEP. Collaborate with CSOs such as the Belize Family Life Association to establish PrEP site and deliver PrEP as part of combination prevention.
5. Develop and update regularly, a shared care protocol between the MOH and the Private Sector and CSOs on PrEP delivery.
6.Train and retrain health care workers in the public and private sector to deliver pre- exposure prophylaxis
7. Develop standard operating procedures and other PrEP job aids
8. Develop and implement a communication Campaign to create demand for PrEP- IEC materials, mass media and digital media.
9. Review the BHIS to ensure the presence of key elements to adequately monitor and report on PrEP programming
10. Incorporate and conduct an annual review of the PrEP programme ( integrated with the review of the prevention programme)
Prevent HIV infection with Post Exposure Prophylaxis | Implement a Post Exposure Prophylaxis for Occupational and Non- occupational Exposure to HIV | 1. Review and regularly update guidelines on post exposure prophylaxis
2. Establish PEP sites/ Integrate PEP delivery into PHC
3. Develop and implement MoU with the Private Health Sector and CSOs to deliver PEP. Collaborate with CSOs such as the Belize Family Life Association to establish PEP site and deliver PEP as part of combination prevention.
4. Develop and update regularly, a shared care protocol between the MOH and the Private Sector and CSOs on PEP delivery.
5. Develop Guidelines, protocols and normative guidance for Pre-exposure prophylaxis. Integrate STI/ VH screening and referral.
6. Train and retrain health care workers in the public and private sector to deliver pre- exposure prophylaxis
7. Develop standard operating procedures and other PrEP job aids
8. Develop and implement a communication Campaign to create demand for PrEP- IEC materials, mass media and digital media.
Eliminate Mother to Child Transmission of HIV/Syphilis and Hepatitis B | Maintain EMTCT initiatives for HIV and Syphillis and scale up Hepatitis B screening | 1. Conduct HIV/STI/ VH counselling and testing for all pregnant as part of antenatal menu of testing
2. Provid counselling and early treatment for all women tested positive for HIV/ STI/VH
3. Provide early treatment for HIV/Syphiliis for the exposed infant
4. Provide full schedule of Hepatits B vaccination including birth dose
5. Test all exposed babies according to national protocol
6. Counsel all HIV positive mothers on caring for the exposed infant and provide formula for exposed infant
7. Conduct ongoing capacity building, coaching and mentoring and supportive supervision of health care workers to counsel, treat and manage HIV infected pregnant mothers
8. Conduct ongoing monitoring visits to improve quality of care and for monitoring and reporting
9. Prepare and submit reports to PAHO/WHO to achieve and maintain elimination status
Prevent TB among people with HIV | Scale up TB/HIV collaborative prevention activities | 1. Review and update and implement Infection Control
2. Establish and support the functioning of the infecton Control Committee
3. Screen all HIV patients and high risk populations for TB based on national protocols
4. Provide INH prophylaxis to all PLHIV, KP and others based on eligibility and national guidelines
Service Delivery for Impact : Treatment, Care and Support
Strengthen governance, accountability and national planning for HIV/STI/VH and TB treatment, support and chronic care | Strenghten coordination for the delivery of HIV/STI/VH and TB treatment, support and chronic care services | 1. Establish National Treatment Technical working group and conduct quarterly meetings for the coordination of treatment, support and chronic care services
2. Conduct quarterly quality assurance/ oversights to public, private and CSO sites delivering HIV/STI/VH and TB treatment.
3. Conduct annual treatment review- identify gaps and opportunities, revise treatment programming and reset treatment targets.
4. Collaboate with Prevention and SI working groups to comprehensively address issues along the prevention and treatment and care continuum including linkage to care
Deliver High Impact package of services for treatment, support and chronic care on HIV/STI/VH and TB | Define and regularly review and update the package of prevention services for Key Populations | 1. Define, review and update annually, package of treatment, support and chronic care services services for HIV/STI/VH and TB focusing on key populations
2. Develop guidelines of the delivery of treatment services for KPs
3. Identify and build capacity of CSOs and Private Sector to deliver the package of treatment of KPs
4. Develop Shared Care Protocol with CSO and Private Sector to deliver the package of treatment services to KPs.
5. Conduct quarterly quality and monitoring and reporting oversight visits to CSOs and Private Sector to esnure compliance with national protocols and guidelines
Expand Treatment Coverage | Scale up treatment for HIV/TB/ VH and STIs. | 1. Provide uninterrupted access to medicines treatment for all patients with HIV/STI/VH and TB and treatment of comorbidities
1. Conduct regular Review and Update of treatment guidelines to incorporate new evidence and approaches for HIV/ STI/ VH and TB
2. Conduct Training and refreshers training of health care workers in the private and public sectors and CSO on treatment guidelines and management of HIV/STI/Vh and TB
3. Print and distribute treatment guidelines, strandard operating procudures and jobs aids
5. Develop and update, in collaboration with CSO, PLHIV and KPs, annual treatment plans that examines and agrees on new appraoches and innovations to the delivery of Treatment and to incorportate new medicines for HIV/STI/VH and TB
6. Develop and implement a shared care protocol with CSO and the privat sector
5. Implement and monitor treatment plans in the public, private and CSO sectors
| Scale Up DTG transitioning and implement Treat All | 1. Develop and implement a transition plan for Treat All and DTG transitioning
Strenghten Linkage to Care | Develop/ Strenghten a peer navigation programme | 1. Develop systems and tools and implement a peer navigation system
2. . Review and update bi-directional referral system to include STIs/VH and TB
3. Train services providers on peer navigation inclucing to conduct client education on the benefits of early treatment
3. Conduct regular peer navigation coordination meetings for knowledge and experience sharing
4. Conduct ongoing monitoring of peer navigation programme
Deliver the highest quality of care | Develop/ Update and implement a quality of care programme | 1. Develop a quality of care programme with continous quality imporvement for HIV/STI/VH and TB with quality of care indicators
2. Establish and support the functioning of a National Quality of Care Committee ( QoC) and site specific QoC Committees ( public, private and CSOs)
2. Train quality improvement teams on continuos quality improvement- planning, implementing, monitorng and adapting for improved outcomes
4. Conduct annual quality of care conference
3. Develop a clinical mentoring and supportive supervison programme
4. Establish team of clinical mentors
5. Conduct onging clinical mentoirng and supportive supervison
6. Conduct client satisfaction survey
7. Develop protocols and tools and implement monitoring of the early warning indicators
| Develop/Update and Implement a treatment literacy programme | 1. Develop treatment literacy manual and tools
2. Train service providers at public, private and CSO sites to delivery treatmemt literacy
3. Produced IEC materials - posters, brochures and audiovisuals to suuport treatment literacy
4. Build cadre of people affected by HIV/STI/VH and TB as treatment advocates.
| Scale up outreach and community response to support TB and TB/HIV treatment | 1. Develop/ Update and implement a DOTS strategy to incorporate HIV/STI/VH
2. Develop and update protocols for DOTS to incorporate HIV/STI/VH
3. Collaborate with CSOs to support DOT in the community, for KPs and PLHIV
3. Train Health Care staff in the public, private and CSOs sector in the provision of DOTS
4. Develop tools and incorportate DOTS montorng into the BHIS
5. Conduct monthly review of DOTS programme
6. Evaluate the effectiveness and impact of an integrated DOTS programme
| Deliver innovative approaches to enhance adherence to treatment for HIV/STI/VH and TB including treatment literacy. Multi months dispensing, treatment pick up and community follow up | 1. Review and Update Adherence Strategy
2. Train and Retrain Social Workers/ counsellors/ peer eductars in the public and private sectors on adherence strategies and tools
3. Collaborate- train, support and monitor- with CSOs to support community follow up of person of treatment the monitoring of adherence for HIV and TB in KPs
4. Develop tools and incorportate adherence monioring into the BHIS
5. Conduct monthly adherence case management session with private, public and CSO sector to discuss challenges with adherence, strategies implemented across sites and lessons learned
Strenghten laboatory services for timely quality assured diagnosis and treatment moitoring | Scale up the use of new techncology for rapid results | 1. Review and update laboratory policies will be reviewed and updated to reflect the expansion rapid diagnostics.
2. Procure and implement point of care testing for STIs
3. Scale up the use of GeneXpert of MTB diagnosis and RR and HIV Viral load testing
4. Stregnthen drug resistance monitoring for HIV/STI/TB
5. Continue with ongoing testing for the diagnosis of opportunitics infections and mornitoirng of co mrbidt conditions
Support chronic care people with HIV/STI/VH and TB | Provide psychosocial, nutritional, economic and other forms of support for people with HIV/STI/VH and TB | 1. Train and retrain social workers/ counsellors/ peer educators to provide counselling and relevant referrals for people with HIV/STIs/VH andTB
2. Scale up and support peer support networks
3. Strenghten intersectoral collaboraton to facilitate referrals legal, nutritional, nutritonal, housing, employment, economic and other forms of support
4. Collaborate with CSO to provide follow up support for chronic care
Strategic Direction 3: Delivery for Equity
Creating an enabling Environment for equitable of services to all persons including KPs | Policy Reforms, Laws and Regulation | 1. Conduct ongoing advocacy for the passing of the Equal Opportunities Bill, National Gender Policy and others that are pro health and relevant to HIV/STI/VH and TB
| Removing institutional and service delivery barriers | 1. Develop policies and practices for the health care system geared at removing stigma and discrimination in the health care settings and at community sites
2. Train public and private sector and CSO service providers on Human Rights and on delivering services in a non judgemental way, void of any sigma and discrimination and with respect for all.
3. Conduct Stigma Index survey to meassure stigma and discrimination
4. Sensitise Health Care Workers on Patient Bill of Rights
5. Develop, update and implement guidance and implementation tools on the prevention and management of gender-based violence different populations, including children, adolescents and key
6. Training and retain health care workers on the use of Gillick competency and fraser test for access to SRH services of adolscents
| Strenghten mechanisms for monitoring and reporting and to provide redress for Human Rights Violations | 1. Scale up the Human Rights Observatory for greater government ownership and multi sectoral engagement- CSO, Law enfrocement agenies
2. Procure Computer hardware and IT software to scale up the Human Rights Observatory initiative
3. Link the Human Rights Observatory to the Belize Health Information Systems for comprehensive reporting on risk, human rights violation and disease acquisition and transmission
4. Develop a network of legal practitioners to support redress actions for Human Rights Violations
5. Conduct training and Empower Key Populations, PLHIV to understand their rights, understand when these are violated and mechnisms for reporting violations
6. Develop and implement communication startegies to increase awareness among people with HIV/STI/VH and TB focusing on key populatons when and how to access the redress mechanism
Strenghtening/Addressing Human Resources for Equity |  | 1. Lay counsellors/ testor for HIV/STI/VH and TB
2. Conduct HR assessment for the coordination and management of the MoH response to HIV/STI/TB/VH
3. Conduct assessemnt of the HIV/STI/VH/TB work forced and make recommendations for efficiencies
Supply Chain Management Systems- ensuring supplies of good quality ARVs, STI, TB, VH medicines, diagnostics and supplies- Pool procurement, morbidity forecasting etc | Strenghten Supply Chain Management Systems for HIV/STI/VH and TB medicines, commodities and supplies | 1. Establish a quantification working group to lead quatification process and conduct regular review of stock on hand
2. Conduct annual morbidity quantification and forecasting
3. Procure medicines for HIV/ STIs/ VH and TB that are WHO prequalified
4. Utilise mechanisms such as the PAHO pool procurement and PAHO Startegic Fund
5. Regularly update the list of essential medicines to incorporate new medicines for HIV/STI/ VH and TB
Strategic Direction 4: Financing for Sustainability
Develop and cost an investment case for HIV/STI/VH and TB |  | 1. Develop terms of Reference and establish technical working group to guide the development of the Investment case
2. Develop the investment case with technical leadership from UNAIDS and other techncial agencies
3. Conduct stakeholder consulatation to share approaches and recommendations for smart invetsments with national stakeholders
4. Implement recommendations of the investment case
5. Utilise key findings and recommendations of the investment case to advocate with the political leadesrhip including the Minister of Finance for increased domestic allocation of resources
6. Utilise key findings and recommendations of the investment case to guide funding request to the Global Fund and other funding agencies
7. Prepare policy brief for high level policy makers on the recommendations for smart investments and increase in domestic financing
Estimate resource needs for the HIV/STI/VH and TB response and implement measures to address financial gaps | Conduct costing of the National HIV/STI/VH and TB Plan 2021-2025 | 1. Develop terms of reference and establish a techical working group to guide the costing of the National HIV/STI/VH and TB Plan 2021-2025
2. Hire consultant to develop the costing plan
3. Conduct stakeholder consultation to share the costing plan
4. Conduct advocacy with political leadership including the Minister of Finiance to highlight the funding gaps
| Identify the resource gap and implement measures to bridge the gap | 1. Develop and implement resource mobilisation plan to bridge the reource gap
2. Prepare and submit funding proposal to the Global Fund in 2021 for three years of funding
Provide Financial Protection and Reduce Financial Risk | Engage the Belize National Health Insurance | 1. Establish high level working group to engage with the Belize National Health Insurance
2. Define with the NHI, elements of the essential package of services that will be included in the NHI menu of services
3. Review regulatory frameworks and define mechanisms to include components of the essential package of services for HIV/STI/VH and TB services as part their menu of services for funding
Develop and implement Innovative Financing mechanisms for sustainability | Develop social contracting mechanism with CSO | 1. Review and understand the legal and regulatory needs for social contracting with CSO
2. Determine the appropriate finding mechanisms for social contracting
3. Advocate for transparency and accountability in the contract selection process
Transitioning from donor funding to domestic resources |  | 4. Develop and implement transparent procurement and selection process
5.Ensure adequate, predictable funding for social contracting
6. Develop Systems to fund CSOs- including the development of an MoU or financing Agreement with CSO for social contracting
7. Conduct capacity building- management capacity, techncial implementation and monitoring, reporting and evaluation- for CSO to effectively engage in social contracting
8. Provide funding for pilot social contracting of CSOs
9. Develop and implement systems for montoring and oversight of CSO social contracting
10. Conduct oversight and monitoring visits to CSO
11. Documents results, impact, lessons learnt from pilot funding for scale up for social contracting
12.Conduct regular CSO social contracting coordination meetings
Monitoring of HIV/STI/TB/VH expenditure and cost and cost effectiveness | Conduct regular NHA and NASA ( every two years?) | 1. Develop ToR and Establish Technical working group
2. Conduct NASA
3. Share findings and recommendations of the NASA
4. Implement recommedations of the NASA
| Conduct costing and effectiveness analysis of new strategies-PrEP, Essential Package of Services and Combination Prevention Package of Services for HIV/STI/VH and TB | 1. Develop ToR and Establish Technical Working Group to guide costing and cost analyses exercises
2. Conduct costing and cost analyses
3. Share findings and recommendations of the costing and cost analyses
4. Implement recommendation of the costing and cost analyses
5. Conduct hands on training and mentoring of local team to conduct spending assessments, costing and costing analysis.
Secure reduce prices and increase competitives for medicines, commodities and supplies for HIV/STI/VH and TB |  | 1. Establish a high level working group with partners, donors, Ministry of Finance and other government agencies to address policies that will to reduce prices and greater competitiveness, understand the dynamics and shifts in supply chain and identify opportunties for reduced prices.

## Implementation plan
Belize National HIV/STI/VH and TB Implementation Plan 2021-2025
Priority Strategy | Priority Intervention | Specific Activities | Timelines |  |  |  |  | Lead Agency | Collaborating agencies and partners | Discissions/ Comments
|  |  | 2021 | 2022 | 2023 | 2025 | 2025
STRATEGIC PRIORITY AREA 1: Information for Tailored, Targeted and People Centered Response
Strategic Objective 1.1 : Strengthen and Decentralise Belize Health Information System for comprehensive data to adequately monitor and respond to HIV/STI/VH and TB by 2025
|  |  | Yr1 | Yr2 | Yr2 | Yr4 | Yr 5 | Lead Agency | Collabroating Agency | Discussions/comments
Strengthen Routine Data Collection by maximizing the use of the BHIS | Scale up the use of the BHIS to the private health sector and CSOs | 1. Complete the review of the BHIS for comprehensive monitoring and reporting for HIV/STI/VH and TB | x | x | x | x | x | MoHW | PR, CSO, Private sector | Please specify with CSOs and Private sectors.
|  | 3. Conduct training and ongoing supervision on the use of the BHIS | x | x | x | x | x | MoHW | PR, CSO, Private sector
|  | 4. Conduct training on site specific data analysis for service delivery improvement |  | x | x | x | x | MoHWW | PR, CSO, Private sector
|  | 5. Assessment of providers to understand their IT capacity and bottlenecks that prevent reporting on HIV/STI/VH and TB | x |  |  |  |  | MoHW | PR, CSO, Private sector
| Generate more granular , high quality data for action | 1. Review the integrated patient montoring system to ensure that all data elements are captured and incorporated into the BHIS for comprehensive reporting for HIV/STI/VH and TB | X | x |  | x |  | MoHW | NAC, PR, PAHO | This will be to support the current review process as well as for any ongoing data needs based reporting requirements
|  | 2. Conduct training and support service delivery sites to routinely generate site specific care cascades for HIV/STI/VH and TB for specific populations including MSM,Sex Workers, Transgender Persons, Migrants, Men and others and to use the cascade analyses to improve service delivery |  | x |  | x |  | MoHW | NAC, PR,PAHO
| Generate aggregrate data to understand the burden of the disease | 1. Generate incidence, prevalence and mortality data on a regular basis to understand the burden of the HIV/STI/VH and TB and the impact of the response. | x | x | x | x | x | MoHW | HIV/ST/TB. VH from yr 2
|  | 2. Generate prevalence data on co- infections and co morbid conditons for programme planning | x | x | x | x | x | MoHW
|  | 3. Generate data on the social, economic, cultural and other factors that correlates with risk for HIV/STI/VH and TB and use data for policy development to strenghten implementation across sectors and disciplines. | x | x | x | x | x | MoHW
| Monitor the impact of PrEP | 1. Develop tools, collect data and monitor the PrEP pilot initiative | X | X |  |  |  | MoHW | PAHO | The work on PrEP has just commenced. This willcontinue in the new year and a pilot will be initated in the second year after which this will be scaled up.
|  | 2.Update data collection tools and systems for the scale up and to monitor the impact of PrEP |  |  | X | X | X | MoHW | CSO
Strategic Objective 1.2: Generate annual care cascades disaggregated by sub populations, age-group and geographic locations
Improve monitoring along the care cascade | Develop Care Cascades | 1. Generate cascades for different populations (MSM, transgender persons, migrant populations, adolescents, men, the general population) and disaggregated by gender, agegroups and health districts or geographic location | x | x | x | x | x | MoHW | NAC, CSO, Private Sector
|  | 2. Conduct training and annual refreshers training for CSOs and service providers to generate site specific care cascades by populations, agegroups and others and to conduct cascade analyses for programme improvement | x | x | x | x | x | MoHW | NAC,CSO, Private Sector
Strategic Objective 1.3: Increase the understanding of gonococcal antimicrobial resistance, HIV drug resistance and Multidrug Resistant TB and establish second generation surveillance by the end of 2025
Strenghten surveillance for Gonococcal resistance, HIV DR and MDR TB | Conduct special studies to determined prevalence and resistance patterns for gonococcal, HIV and TB infections | 1. Establish TWG, develop potocol and implement HIVDR survey | x |  |  |  | x | MoHW | Technical partners ( PAHO and others) | Hwo about having a second survey in the final year?
|  | 2. Conduct Data analysis, develop report and share survey findings | x | x |  |  | x | MoHW | Technical partners ( PAHO and others) | This is rolled over to the second year if necessary
|  | 3. Develop a dissemination plan to share findings of the survey. | x | x |  |  | x | MoHW | Technical partners ( PAHO and others)
|  | 4. Liaise with the Treatment Working Group to discuss findings and recommendation to guide changes to treatment guidelines and protocols | X | X |  |  | X |  | Technical partners ( PAHO and others)
|  | 5. Conduct Gonococcal antimicrobial resistance study |  | x |  |  |  | MoHW | Technical partners ( PAHO and others)
| Establish second generation surveillance | 1. Conduct a review of the surveillance system to understand the gaps and needs for second generation surveillance | X |  |  |  |  | MoHW | Technical partners ( PAHO and others)
|  | 2. Update surveillance systems to facilitate second generation surveillance- review of surveillance manual, roles and responsibilities of persons in surveillance, data collection systems and tools |  | x |  |  |  | MoHW | Technical partners ( PAHO and others)
Stregnthen laboratory capacity for resistance testing for HIV/GC and TB | Strengthen laboratory quality assurance | 1.Update laboratory policy to include menu of testing and quality assurance for HIVDR , GC anitmicrobial resistance and MDR TB | x |  |  |  |  | MoHW | PAHO, Reference Laboratory, Mexico, CMLF
|  | 2. Train and conduct refreshers training for laboratory personnel to conduct testing | x |  | x |  | x | MoHW | PAHO, Reference Laboratory, Mexico, CMLF
|  | 3. Develop quality assurance protocols and standard operating procedures |  | x |  |  |  | MoHW | PAHO, Reference Laboratory, Mexico, CMLF
|  | 4. Develop and implement systems to monitor laboratory quality assurance for HIVDR, GC antimicrobial resistance and MDR TB |  | x |  |  |  | MoHW | PAHO, Reference Laboratory, Mexico, CMLF
|  | 5. Train laboratory QA officers to conduct routine QA as well to support external QA |  | x |  | x |  |  | PAHO, Reference Laboratory, Mexico, CMLF
Strategic Objective 1.4: Strengthen data protection of data generated by routine data collection systems and special surveys for privacy, confidentiality and safety.
Ensure data protection and client and community safety | Strengthen data protection systems for collecting, storing and reporting data | 1. Develop and adapt data protection policy | x |  |  |  |  | MoHW | Technical Partners (PAHO and others), SIB
|  | 2. Develop update and review normative guidance and protocols ( including clear definitions of roles and levels of responsibilities for data managers) on data protection |  | x |  |  |  | MoHW | Technical Partners (PAHO and others), SIB
| Build capacity on confidential data collection,storage and sharing | 3. Train data collector, users, managers and health care worker on data confidentiality in collecting, storing and sharing of data |  | x |  | x |  | MoHW | Technical Partners (PAHO and others), SIB
|  | 4. Establish a cadre of Principal Investigators who are trained on data protection and confidentiality. |  | x |  | x |  | MoHW | Technical Partners (PAHO and others), SIB
| Address breaches in data confidentiality | 5. Develop and apply standard operating procudures for breaches in data confidentiality. |  | x |  |  |  | MoHW | Technical Partners (PAHO and others), SIB
Ensure high data quality | Implement systems for data quality review | 1. Develop data quality manual |  | x
|  | 2. Conduct training on data quality for facility and regional level staff. |  | x |  | x |  | MoHW | Technical partners (PAHO and Other), SIB, NAC | Assumption- staff is available
|  | 3. Train data managers on the use of data quality tools such as WHO excel data quality tool |  | x |  | x |  | MoHW | Technical partners (PAHO and Other), SIB, NAC
|  | 4. Conduct ongoing quarterly supportive supervision for data quality | x | x | x | x | x | MoHW | Technical partners (PAHO and Other), SIB, NAC | This could be one or two M&E officers from MoHW, PAHO and the NAC who conduct the supportive supervision
|  | 5. Conduct periodic data quality reviews at the facility, regional and national levels | [5 empty] | MoHW | Technical partners (PAHO and Other), SIB, NAC
Strategic Objective 1.5: Enable and strengthen the capacity to conduct research by the end of 2025
Enable and Promote Research |  | 1. Develop, cost and implement a research agenda | x |  |  |  |  | NAC | MoHW, Technical Partner, University of Belize, UWI, SIB, MoE, CSOs | Allocation of resources to conduct the studies
|  | 2. Collaborate with tertiary institutions to conduct research that adds to the pool of knowledge on HIV/STI/VH and TB | x | x | x | x | x | NAC | MoHW, Technical Partner, University of Belize, UWI, SIB, MoE, CSOs | CSOs have also done research- operatons research
|  | 3. Build capacity to conduct research including protocol development, research ethics, quantitative and qualitative data analysis |  | x |  | x |  | NAC | MoHW, Technical Partner, University of Belize, UWI, SIB, MoE, CSOs
|  | 4. Train and establish a cadre of principal investigators |  | x |  | x |  | NAC | MoHW, Technical Partner, University of Belize, UWI, SIB, MoE, CSOs
Strategic Objective1. 6: Strengthen Governance and Accountability for Strategic Information.
Enhance governance mechanism for Strategic Information | Establish Strategic Information Working Group | 1. Establish Broad Based Strategic Information Technical Working | x |  |  |  |  | MoHW and NAC | Technical partners, CSO, KPs, PLHIV, SIB, non- health ministries | This ultimately will be dependent on the ToR for this group
|  | 2. Convene semi-annual meetings of the SI working group | x | x | x | x | x | MoHW and NAC
|  | 3. Conduct ongoing advocacy for policy development, programme planning and resource mibilisations based on data | X | x | x | x | x | SI Working Group
|  | 4. Liasie with othet technical working groups ( prevention and treatment) to examine SI data including data traingulated from different sources for a client centered response. | x | x | x | x | x | SI Working Group
| Strenghten policy, governance and programmatic functions | 1. Conduct WHO Multisectoral Accountability Framework for TB | x |  | x |  |  | MoHW, NAC and SI Working Group
|  | 2. Apply National Policy and Commitment Index as part of the GAM reporting process. | x |  | x |  |  | MoHW, NAC and SI Working Group
Enhance data collection, analysis and reporting | Strengthen functional roles and responsibilities for data collection, analysis and reporting | 1. Conduct a review of the surveillance systems for collecting, analysis and reporting for comprehensive data collection for HIV/STI/VH and TB |  | x |  |  |  | MoHW | Technical partners (PAHO)
|  | 2. Review and update surveillance manual, standard operating procedures, guidelines and tools for data collection, analysis and reporting, including clear definition of roles and responsibilities |  |  | x |  |  | MoHW | Technical partners (PAHO)
| Strenghten data sharing | 1. Develop and maintain data dash boards with current on prevalence, incidence, impact and coverage outcomes as well as care cascades that is available to all stakeholders | x | x | x | x | x | MoHW | NAC, Technical partners (PAHO)
| Strenghten data driven multistakeholder programme planning | 1. Conduct annual Multi- stakeholder data sharing forum and annual programme review and planning. | x | x | x | x | x | MoHW/NAC/SI working Group | Technical partner, CSO
|  | 2. Conduct annual target review and target setting process | x | x | x | x | x | MoHW/NAC/SI working Group | Technical partner, CSO
|  | 3. Conduct mid-term and end of term reviews of the National HIV/STI/VH and TB strategic Plan 2021-2015 |  |  | X |  | X | MoHW/NAC/SI working Group | Technical partners, CSOs.
| Report on Global Commitments | 1. Conduct nation estimation processes for HIV and TB in collabroation with UNAIDS , PAHO. CSO and other stakeholders | x | x | x | x | x | MoHW/NAC/SI working Group | Technical partner, CSO
|  | 2. Submit timely reports to UNAIDS Global AIDS Monitoring Progess, WHO Universal Access and Stop TB initative | x | x | x | x | x | MoHW/NAC/SI working Group | Technical partner, CSO
STRATEGIC PRIORITY AREA 2 : QUALITY AND EFFICIENT SERVICE DELIVERY FOR IMPACT
PREVENTION
Strategic Objective 2.1: Tailored combination prevention package of services that integrates HIV/STI/VH and TB is delivered to all persons and focused on adolescents, young adults women and girls and men
Behaviour Change Communiction for Risk reductiuon | Develop and implement BCC plan | 1. Develop, update and implement a Integrated Behaviour Change Communication Plan for HIV/STI/VH and TB. Implement content appropriate BCC campaigns for adolsecents, young adults, women, girls and men | x |  |  |  |  | MoHW | NAC, technical partrners, Ministry of Education, Women Affairs Bureau ( Gender Bureau)?
|  | 2. Training Health Care Workers- peer educators, counsellors, social workers on education and counselling risk reduction and behavior change for HIV/STI/VH and TB including condom negotiation use. | x | x | x | x | x | MoHW | NAC, technical partrners, CSO, KPS, PLHIV, adolescents
|  | 3. Monitor the effectiveness and impact of Behaviour Change Communication- Incorporate measurements in population based survey? | [5 empty] | MoHW | NAC, technical partners, SIB
| Scale up Peer education for adolescents and young adults out of school | 1. Increase the number and build capacity of HIV peer educators to conduct integrated (HIV/STI/VH and TB) peer education and risk reductions for adolescents and young adults out of school | x | x | x | x | x | MoHW | NAC, CSO
|  | 2. Review peer educators guidelines/ manuals/SOPs/ documentation to include an integrated- HIV/STI/VH and TV approach-to peer education | x | x |  |  |  | MoHW | NAC, CSO
|  | 3.Conduct regular/ quarterly meetings of the network of peer educators to share experiences and lessons learned | x | x | x | x | x | MoHW | NAC, CSO
| Develop and deliver multi media information and education campaigns | 1. Test, adapt and produce culturally appropriate messages for different sub populations such as adolecents, young MSM and Young Transgender persons | X | x | x | x | x | MoHW | NAC, CSO
|  | 2. Disseminate information and message using new media such as instagram, whats app and text phone messaging | x | x | x | x | x | CSO | NAC. MoHW
|  | 3. Scale up and expand the network of cyber educators to conduct risk reduction counselling for young MSM and TG persons who frequent targeted websites. | x | x | x | x | x | CSO Hub | NAC, MoHW
Strenghten Health and Family Life Education and Comprehensive Sexuality Education | Scale up HFLE and CSE to inschool adolscents and yound adulst | 1. Conduct review of HFLE and CSE curriculum |  | x |  |  |  | MoE | MoHW, CSO, University of Belize
|  | 2.Conduct pre-service and in-service training for teachers and school counsellors to deliver HFLE and CSE |  |  | x | x | x | University of Belize | MoE, CSO
|  | 3. Empower parents through Parenting conferences to engage their children on HFLE and CSE |  |  | x | x | x | MoEYSC | CSO, NAC, MoHW
|  | 4. Expand the network and build capacity of school HIV peer educators to address other issues such as bulling/ cyber bulling, STI counseling and others | x | x | x | x | x | MoEYSC | CSO, MoHW, NAC
|  | 5. Establish school health clubs | x | x | x | x | x | MoEYSC | CSO, MoHW, NAC
Strenghten Sexual and Reproductive Health Services | Expand the menu of SRH services | 1. Conduct regulat review of the pacakge of SRH services to incorporate new technology such as STI screening and counselling, syphilis testing, Hepatitis B and C testing, HPV screening , Visual Inspection with Acetic Acid, PAP smear, Hepatitis B vaccination and HPV vaccination | x |  |  |  |  | MoHW | NAC, CSO
|  | 2. Review HPV vaccination policy to include vaccination of boys | x | x |  |  |  | MoHW | NAC, CSO
|  | 3. Develop communication campaigns to dispell myths and misconcpetions of and increase demand for HPV vaccination for boys and girls | x | x | x | x | x | MoHW | NAC, CSO
|  | 4. Deliver full course of HPV vaccination for all eligible boys and girls |  |  | x | x | x | MoHW
|  | 5. Conduct continous and ongoing programme monitoring of the HPV vaccination programme | x | x | x | x | x | MoHW | CSO, NAC, MoHW
|  | 6. Vaccinate all eligible unvaccinated adolescents and young adults with full course of Hepatitis B vaccine | x | x | x | x | x | MoHW | CSO
|  | 7. Train and retain health care workers on delivering non judge mental, unbiased SRH services to adolescents and young adults using the Gillick Competency and Fraser Test | x | x | x | x | x | MoHW | CSO
|  | 8. Establish, staff and support the functioning Youth Friendly Health Spaces including at CSOs that is focused on SRH services for young MSM and TG persons | x | x | x | x | x | MoHW | CSO
|  | 9. Develop and support programmes for teenage parents | x | x | x | x | x | MoHW and MoEYSC | CSO
|  | 10. Reintegrate teenage parents for completion of secondary school | x | x | x | x | x | MoEYSC | MoHW, CSO
Address Gender Based Violence and Sexual Violence |  | 1. Develop, implement and monitor communication campaigns to prevent primary and secondary GBV and sexual violence | x | x | x | x | x | Ministry of Human Development, Womens Department, | National Womens Commission, NAC. MoHW, CSO
|  | 2. Develop, implement and monitor communication campaign for victims of abuse to understand the steps in accessing care and reporting. | x | x | x | x | x | Ministry of Human Development, Womens Department, | National Womens Commission, NAC. MoHW, CSO
|  | 3. Train health care staff in public, CSO and private health sector provide sensitive health care services to victims including counselling, psychosocial support and other counselling | x | x | x | x | x | MoHW | NAC, CSO
|  | 4. Strenghten referral services for legal support | x | x | x | x | x | MoHWand AG Ministry | CSO
|  | 5. Update Policy and treatment guidelines and offer post exposure prophylaxis for HIV and STI to eligible persons who experience sexual abuse. | x | x | x | x | x | MoHW | CSO
Strategic Objective 2.2: Tailored combination prevention package of services that integrates HIV/STI/VH and TB is delivered to MSM, TG persons and their sex partners.
Deliver High Impact Combination Prevention on HIV/STI/VH and TB | Define and regularly review and update the package of prevention services for Key Populations | 1. Define, review and update annually, package of prevention services for HIV/STI/VH and TB focusing on key populations | x | x | x | x | x | MoHW | NAC,CSOs, technical partners (PAHO)
|  | 2. Develop guidelines of the delivery of prevention services for KPs | x | x | x | x | x | MoHW | NAC,CSOs, technical partners (PAHO)
| Greater engagment of CSOs in service delivery for KPs | 3. Identify and build capacity of CSOs and Private Sector to deliver the package of prevention services of KPs | x | x | x | x | x | MoHW | NAC, Technical partners,CSO
|  | 4. Develop MoU with CSO and Private Sector to deliver the package of prevention services to KPs. | X |  |  |  |  | MoHW/CSO | NAC
|  | 5. Conduct quarterly quality and monitoring and reporting oversight visits to CSOs and Private Sector | x | x | x | x | x | MoHW/CSO | NAC
|  | 6. Conduct quarterly KP programme review with KPs, CSO, Private sector and Health Care workers | x | x | x | x | x | MoHW/CSO | NAC
| Develop BCC initatives to increase reduce risk and increase uptake of services | 1. Develop and implement BCC startegy to reduce risk behaviours and increase uptake of prevention services for MSM, TG , Sex Workers, Migrants | x | x | x | x | x | MoHW/CSO | NAC
|  | 2. Implement communication initiatives on social media and via other relevant channels to reduce risk and increase of services | x | x | x | x | x | MoHW/CSO | NAC
Intensify condom programming | Increase access to male and female condoms and lubricants | 1. Review, update and implement national condom strategy | x | x | x | x | x | MoHW | NAC, CSO, technical partners
|  | 2. Develop/ Review and implement condom marketing strategy for increased condom uptake and use | x | x | x | x | x | MoHW | NAC/CSO/technical partners
|  | 3. Train peer educators and health care staff to educate KPs to conduct education on the correct use and consistent of condoms | x | x | x | x | x | MoHW | CSO
|  | 4. Provide quality assured condoms and Lubricants to CSO for KPs | x | x | x | x | x | MoHW
Strategic Objective 2.3: Increase uptake of new prevention modalities including Pre-Exposure prophylaxis - PrEP, PEP, Hepatitis B, Hepatitis C and TB screening for MSM, Transgender persons, sex workers and migrants
Prevent HIV infection with Pre-Exposure Prophylaxis | Develop and Implement a HIV Pre-Exposure Prophylaxis programme | 1. Conduct costing analysis for HIV PrEP to understand the cost of PrEP per patient, the impact in averting new HIV infections and the associated long term cost savings | x |  |  |  |  | MoHW | NAC, CSO, technical partners
|  | 2. Develop and adopt PrEP policy. | x |  |  |  |  | MoHW | NAC, CSO, techncical partners
|  | 3. Develop Guidelines, protocols and normative guidance for Pre-exposure prophylaxis. Integrate STI, Syphilis and Hepatitis B and Hepatitis C screening and referral as part of PrEP. |  | x |  |  |  | MoHW | Technical partners
|  | 4. Conduct PrEP Pilot: Develop and implement MoU with the Private Health Sector and CSOs to deliver PrEP. Collaborate with CSOs such as the Belize Family Life Association to establish PrEP site and deliver PrEP as part of combination prevention. |  | x |  |  |  | MoHW | NAC, CSO, technical partners
|  | 5. Conduct monitoring of PrEP pilot, document lessons learned |  | x |  |  |  | MoHW | NAC, CSO, technical partners
|  | 6. Scale up PrEP for national coverage |  |  | x | x | x | MoHW | NAC, CSO, technical partners
|  | 7. Develop and update regularly shared care protocol between the MoHW and the Private Sector and CSOs on PrEP delivery. |  |  | x | x | x | MoHW | NAC, CSO, technical partners
|  | 8.Train and retrain health care workers in the public and private sector to deliver pre- exposure prophylaxis |  |  | x | x | x | MoHW | NAC, CSO, technical partners
|  | 9. Develop and implement a communication Campaign to create demand for PrEP- IEC materials, mass media and digital media. |  |  | x | x | x | MoHW | NAC, CSO, technical partners
|  | 10. Incorporate and conduct an annual review of the PrEP programme ( integrated with the review of the prevention programme) |  |  | x | x | x | MoHW | NAC, CSO, technical partners
Prevent HIV infection with Post Exposure Prophylaxis | Implement a Post Exposure Prophylaxis for Occupational and Non- occupational Exposure to HIV | 1. Review and regularly update guidelines on post exposure prophylaxis to include nPEP | x |  | x |  | x | MoHW | Technical partners
|  | 2. Develop and implement MoU with the Private Health Sector and CSOs to deliver PEP and nPEP. Collaborate with CSOs such as the Belize Family Life Association to establish PEP site and deliver PEP as part of combination prevention. | x |  |  |  |  | MoHW | NAC/CSO/technical partners
|  | 3. Develop Guidelines, protocols and normative guidance for Pre-exposure prophylaxis. Integrate STI/Syphilis and Hepatitis B and C screening and referral. | x |  | x |  | x | MoHW | Technical partners
|  | 6. Train and retrain health care workers in the public and private sector to deliver post exposure prophylaxis | x | x | x | x | x | MoHW | Technical Partners
Ensure access to Hepatitis B Vaccinations | Scale up access to Hepatitis B vaccine | 1. Review and update protocols for to expand access to Hepatitis B vaccines to include all unvaccinated children, adults are high risk for infections- MSM and TG | x |  |  | x |  | MoHW | Technical partners
|  | 2. Develop and implement communication strategy to increase the uptake of Hepatitis B vaccines | x | x | x | x | x | MoHW | CSO
|  | 3. Train public and private health care workers on counselling and client education on Hepatitis B | x | x | x | x | x | MoHW | CSO
|  | 4. Develop IEC materials for Hepatitis B vaccines | x | x | x | x | x | MoHW | CSO
|  | 5. Vaccinate all eligible persons with full course of Hepatitis B vaccine | x | x | x | x | x | MoHW | CSO
Strategic Objective 2.4: Increase uptake of new testing modalities, such as HIV self- testing and community based testing, for screening and diagnosis of HIV/STI/VH/TB.
Scale up quality assured HIV/STI/VH and TB testing using new approaches with better yield to reach the most at risk populations | Scale up HIV testing to reach for better yield | 1. Using WHO six step appraoch, review and update testing policy, strategy, guidelines and protocols to include new testing approaches- HIV self -testing, routine testing in some situation, PITC, and community based testing and the role of lay testers in expanding testing services | x |  |  |  |  | MoHW | NAC/CSO/technical partners
|  | 2. Train and retrain testing staff ( public and private health sectors and CSOs) on HIV/STI/TB testing protocols including the 5 Cs of HIV testing- consent, confidentiality, counselling, correct test results and connections to care, treatment and prevention services. | x | x | x | x | x | MoHW | NAC/CSO/technical partners
|  | 3. Develop and implement communication to strategies to create demand for testing among men. | x | x | x | x | x | MoHW | NAC/CSO/technical partners
| Diversify testing approaches to include newer and more effective modalities such as HIV self-testing and community- based testing, provider- initiated testing that integrates HIV/STI/VH and TB testing | 1. Develop a HIV self- testing policy | x |  |  |  |  | MoHW | NAC/CSO/technical partners
|  | 2. Conduct pilot HIV self-testing for KPS. |  | x |  |  |  | MoHW | NAC/CSO/technical partners
|  | 3. Conduct an evaluation of the HIV Self Testing Pilot. |  | x |  |  |  | MoHW | NAC/CSO/Technical partners
|  | 4. Scale up self testing for national coverage |  |  | x | x | x | MoHW | NAC/CSO/technical partners
|  | 5. Train and retrain CSOs on HIV self-testing |  | x | x | x | x | MoHW | NAC/CSO/technical partners
|  | 6. Develop tools, IEC materials for KPs to understand the self-testing process/ steps in self testing. |  | x |  |  |  | MoHW | NAC/CSO/technical partners
|  | 7. Develop reporting mechanisms and tools for reporting on self-testing to the national programme |  | x |  |  |  | MoHW | NAC/CSO/technical partners
|  | 8. Support CSOs for community-based testing, including index based tested and assisted partner notification |  | x | x | x | x | MoHW | NAC/CSO/technical partners
| Ensure quality assured testing | 1. Review and update quality protocols | x |  | x |  |  | MoHW | Technical partners
|  | 2. Implement and monitor quality protocols | x |  | x |  | x | MoHW | Technical partners
|  | 3. Train laboratory staff and testing and field staff on quality protocols | x |  | x |  | x | MoHW | Technical partners
Reach, counsel and test all contacts of persons with HIV/STI/VH and TB | Conduct contact tracing for all contacts with HIV/STI/VH and TB | 1. Develop and update outreach manual/ contact tracing manual for outreach to contacts of HIV/STI/VH and TB | x |  |  | x |  | MoHW | NAC/CSO/technical partners
|  | 2. Train and Retrain Health Care and community workers on protocols for contact tracing including client confidentiality | x | x | x | x | x | MoHW | NAC/CSO/technical partners
|  | 3. Update all tools for contact tracing such as client intake, daily log, monthly reports and others | x | x | x | x | x | MoHW | NAC/CSO/technical partners
Strategic Objective 2.5: All blood and blood products will be screened for HIV/STIs/VH and other infectious markers
Ensure all Blood and Blood products are safe for transfusion | Screen all blood and blood products are screen for HIV/STI/ VH based on national protocols | 1. Screen all blood and blood products for HIV, STI, Syphilis, Hepatitis B and Hepatitis CV other infectious markers. | x | x | x | x | x | MoHW
|  | 2. Conduct ongoing quality assurance and quality control for blood screening for HIV/STI/Syphilis,Hepatitis B and Hepatitis C and other infectious markers | x | x | x | x | x | MoHW
Startegic Objective 2.6: The burden of TB among PLHIV is reduced with increased TB case findings and IPT prophylaxis and enhanced infection control practices.
Prevent TB among people with HIV | Scale up TB/HIV collaborative prevention activities | 1. Review and update and implement Infection Control Protocols and Practices | x |  |  |  |  | MoHW | Technical partners
|  | 2. Establish and support the functioning of the infection Control Committee | x | x | x | x | x | MoHW | Technical partners
|  | 3. Screen all HIV patients and high risk populations for TB based on national protocols | x | x | x | x | x | MoHW
|  | 4. Provide INH prophylaxis to all PLHIV, KP and others with TB infection based on eligibility and national guidelines | x | x | x | x | x | MoHW
|  | 5. Scale up diagnosis for TB RR TB and MDRTB using GeneXpert and enhance laboratory capacity | x | x | x | x | x | MoHW | Technical partners
Strategic Objective 2.7: EMTCT is scaled up with 100% coverage for HIV, Syphilis and Hepatitis B testing and the management of infected mothers and exposed infant by the end of 2025.
Eliminate Mother to Child Transmission of HIV/Syphilis and Hepatitis B | Maintain EMTCT initiatives for HIV and Syphilis and scale up Hepatitis B screening | 1. Conduct HIV/STI/ VH counselling and testing for all pregnant as part of antenatal menu of testing | x | x | x | x | x | MoHW
|  | 2. Provide counselling and early treatment for all women tested positive for HIV/ STI/VH | x | x | x | x | x | MoHW
|  | 3. Provide early treatment for HIV/Syphilis for the exposed infant | x | x | x | x | x | MoHW
|  | 4. Provide full schedule of Hepatitis B vaccination including birth dose | x | x | x | x | x | MoHW
|  | 5. Test all exposed babies according to national protocol | x | x | x | x | x | MoHW
|  | 6. Counsel all HIV positive mothers on caring for the exposed infant and provide formula for exposed infant | x | x | x | x | x | MoHW
|  | 7. Conduct ongoing capacity building, coaching and mentoring and supportive supervision of health care workers to counsel, treat and manage HIV infected pregnant mothers | x | x | x | x | x | MoHW
|  | 8. Conduct ongoing monitoring visits to improve quality of care and for monitoring and reporting | x | x | x | x | x | MoHW
|  | 9. Prepare and submit reports to PAHO/WHO to achieve and maintain elimination status | x | x |  |  |  | MoHW | Technical partners
Strategic Objective2.8: Enhanced governance and accountability for integrated HIV/STI/VH and TB prevention
Strengthen governance, accountability and national planning for HIV/STI/VH and TB | Strengthen coordination for the delivery of HIV/STI/VH and TB prevention services | 1. Establish National Prevention Technical working group and conduct quarterly meetings for coordination of prevention services | x |  |  |  |  | MoHW | NAC/CSO/Techncial partners
|  | 2. Conduct quarterly quality assurance/ oversights to public, private and CSO sites delivering HIV/STI/VH and TB prevention services. | x | x | x | x | x | MoHW | NAC/CSO/Techncial partners
|  | 3. Prepare and share annual prevention report | x | x | x | x | x | MoHW | NAC/CSO/Techncial partners
|  | 4. Conduct annual prevention review- identify gaps and opportunities, revise prevention programming and reset prevention targets | x | x | x | x | x | MoHW | NAC/CSO/Techncial partners
|  | 5. Liaise with Treatment and SI working groups to comprehensively address issues along the prevention and treatment and care continuum | x | x | x | x | x | MoHW | NAC/CSO/Techncial partners
Quality and Efficient Service Delivery for Impact : Treatment, Care and Support
Strategic Objective 2.9: Strengthen Linkage to Care for persons testing positive for HIV/STI/VH and TB through expanded community outreach and greater engagement of CSOs.
Strengthen Linkage to Care | Develop/ Strengthen a peer navigation programme | 1. Develop systems and tools, peer navigation manual and implement a peer navigation system | x | x | x | x | x | MoHW | CSO
|  | 2. Review and strenghten bi-directional referral system to include STIs/VH and TB | x | x | x | x | x | MoHW | CSO
|  | 3. Train HIV counselors on treatment education including the benefits of early treatment | x | x | x | x | x | MoHW | CSO
|  | 4. Conduct regular peer navigation coordination meetings for knowledge and experience sharing | x | x | x | x | x | MoHW | CSO
Strategic Objective 2.10: Expand treatment coverage for HIV/STI/VH and TB through the delivery of optimize, decentralized treatment using differentiated models of care.
Deliver High Impact package of services for treatment, support and chronic care for HIV/STI/VH and TB | Define and regularly review and update the package of treatment services for Key Populations | 1. Define, review and update annually, package of treatment, support and chronic care services for HIV/STI/VH and TB focusing on key populations | x | x | x | x | x | MoHW | NAC/CSO/Technical partners
|  | 2. Develop and review guidelines of the delivery of treatment services for KPs |  | x |  | x |  | MoHW | NAC/CSO/Technical partners
|  | 3. Identify and build capacity of CSOs and Private Sector to deliver the package of treatment of KPs | x |  |  |  |  | MoHW | NAC/CSO/Technical partners
|  | 4. Develop Shared Care Protocol with CSO and Private Sector to deliver the package of treatment services to KPs. | x |  |  |  |  | MoHW | NAC/CSO/Technical partners
|  | 5. Conduct quarterly quality, monitoring and reporting oversight visits to CSOs and Private Sector to ensure compliance with national protocols and guidelines | x | x | x | x | x | MoHW | NAC/Technical partners
Expand Treatment Coverage | Scale up treatment for HIV/TB/ VH and STIs. | 1. Develop, implement and monitor treatment plan for intergrated HIV/STI/VH and TB treatment delivery using differentiated models of care | x | x | x | x | x | MoHW | NAC/CSO/Technical partners
|  | 2. Finalise draft HIV Guidelines and implement for Treat All and the use of DTG | x |  |  |  |  | MoHW | Technical partners
|  | 3.Conduct regular Review and Update of treatment guidelines to incorporate new evidence and approaches for HIV/ STI/ VH and TB |  |  | x |  | x | MoHW | Technical partners
|  | 4. Conduct Training and refreshers training of health care workers in the private and public sectors and CSO on treatment guidelines and management of HIV/STI/VH and TB | x | x | x | x | x | MoHW | Technical partners
|  | 5. Develop and update and implement, in collaboration with CSO, PLHIV and KPs, annual treatment plans that examines and agrees on new approaches and innovations to the delivery of Treatment and to incorporate new medicines for HIV/STI/VH and TB | x | x | x | x | x | MoHW | CSO/Techncial partners
|  | 6. Develop and implement a shared care protocol with CSO and the private sector to deliver HIV/STI/VH and TB treatments | x |  |  |  |  | MoHW/CSO
|  | 9. Provide uninterrupted access to medicines treatment for all patients with HIV/STI/VH and TB and treatment of comorbidities | x | x | x | x | x | MoHW
| Scale Up DTG transitioning and implement Treat All | 1. Develop and implement a transition plan for Treat All and DTG transitioning | x | x |  |  |  | MoHW | Technical partners
| Implement Differentiated models of care | 1. Develop systems- tools , protocols, standard operating procedures to roll out differentiated models of care | x | x |  |  |  | MoHW | CSO/Techncial partners
|  | 2. Train service providers on differentaited models of care |  | x |  |  |  | MoHW | Technical partners
|  | 3. Increase client awareness through education and counselling |  | x | x |  |  | MoHW | CSO
Support chronic care people with HIV/STI/VH and TB | Provide psychosocial, nutritional, economic and other forms of support for people with HIV/STI/VH and TB | 1. Train and retrain social workers/ counsellors/ peer educators to provide counselling and relevant referrals for people with HIV/STIs/VH and TB | x | x | x | x | x | MoHW | Techncial partners
2. Scale up and support peer support networks
|  | 3. Strengthen intersectoral collaboration to facilitate referrals legal, nutritional, nutritional, housing, employment, economic and other forms of support | x | x | x | x | x | MoHW | Non health line ministries- Ministry of Housing, Labour,Employment, Human Development and others
|  | 4. Collaborate with CSO to provide follow up support for chronic care | x | x | x | x | x | MoHW and CSO
Strategic Objective 2.11: Deliver innovative approaches to enhance adherence for HIV/STIs/VH and TB including strengthening treatment literacy, multi months dispensing, treatment pick up and community follow- up.
Strengthen adherence for retention on care for HIV and Hepatitis B treatment and treatment completion for TB/STIs and Hepatitis C. | Strenghten adherence systems and monitoring | 1. Review and Update strenghten Systems to implement and monitor the Adherence Strategy | x | x | x | x | x | MoHW | CSO and technical partners
|  | 2. Train and Retrain Social Workers/ counsellors/ peer educators in the public and private sectors on adherence strategies and tools for HIV/STI/VH and TB | x | x | x | x | x | MoHW | CSO and technical partners
|  | 3. Collaborate- train, support and monitor- with CSOs to support community follow up of person of treatment the monitoring of adherence for HIV and TB in KPs | x | x | x | x | x | MoHW | CSO and technical partners
|  | 5. Conduct quarterly adherence case management session with private, public and CSO sector to discuss challenges with adherence, strategies implemented across sites and lessons learned | x | x | x | x | x | MoHW | CSO and technical partners
Empower people with HIV/STI/VH and TB | Develop/Update and Implement a treatment literacy programme | 1. Develop treatment literacy manual and tools | x | x | x | x | x | MoHW | Technical partners, Belize Network of PLHIV
|  | 2. Train service providers at public, private and CSO sites to delivery treatment literacy | x | x | x | x | x | MoHW
|  | 3. Build cadre of people affected by HIV/STI/VH and TB as treatment advocates. | x | x | x | x | x | MoHW
| Implement new approaches to treatment delivery | 1. Develop systems, tools, protocols and standard operating procudures for multi month prescribing, community treatment drop off, family pick up and other innovations to support treatment adherence and for greater programmatic efficiency | x | x | x | x | x | MoHW | CSO/Techncial partners
|  | 2. Increase client awareness through education and counselling | x | x | x | x | x | MoHW | CSOs
Expand and Strenghtend the TB DOTS programme | Scale up outreach and community response to support TB and TB/HIV treatment | 1. Develop/ Update and implement a DOTS strategy to incorporate community treatment support for HIV/STI/VH | x | x | x | x | x | MoHW | CSO
|  | 2. Develop and update DOTS, protocols and tools for an integrated approach to community treatment support for HIV/STI/VH, contact tracing and loss to follow up | x | x | x | x | x | MoHW | CSO
|  | 3. Collaborate with CSOs and private health sector to support DOT in the community, for KPs and PLHIV | x | x | x | x | x | MoHW | CSO
|  | 4. Train Health Care staff in the public, private and CSOs sector in the provision of DOTS | x | x | x | x | x | MoHW | CSO
|  | 5. Conduct monthly review of DOTS programme | x | x | x | x | x | MoHW | CSO
Strategic Objective 2.12: Deliver the highest quality of treatment, care and support for HIV/STI/VH and TB that is based on national standards and guidelines.
Deliver the highest quality of care | Develop/ Update and implement a quality of care programme | 1. Develop a quality of care programme with continuous quality improvement for HIV/STI/VH and TB with quality of care indicators | x | x | x | x | x | MoHW | CSO/Techncial partners
|  | 2. Establish and support the functioning of a National Quality of Care Committee ( QoC) and site specific QoC Committees ( public, private and CSOs) | x | x | x | x | x | MoHW | CSO
|  | 2. Train quality improvement teams on continuous quality improvement- planning, implementing, monitoring and adapting for improved outcomes | x | x | x | x | x | MoHW | Techncial partners
|  | 4. Conduct annual quality of care conference | x | x | x | x | x | MoHW | NAC/CSO/Technical partners
|  | 3. Develop and implement clinical mentoring and supportive supervision programme | x | x | x | x | x | MoHW | Techncial partners
|  | 6. Conduct client satisfaction survey |  | x |  |  | x | MoHW | CSO/Techncial partners
|  | 7. Develop protocols and tools and implement monitoring of the early warning indicators | x | x | x | x | x | MoHW | CSO/Techncial partners
Strategic Objective 2.13: Deliver an optimal menu of quality assured laboratory services to support diagnosis and treatment monitoring for HIV/STI/VH and TB
| Scale up the use of new technology for rapid results | 1. Procure and implement point of care testing for STIs | x | x | x | x | x | MoHW | Technical partners
|  | 2. Scale up the use of GeneXpert of MTB diagnosis and RR and HIV Viral load testing | x | x | x | x | x | MoHW | Technical partners
|  | 3 Continue with ongoing testing for the diagnosis of opportunities infections and monitoring of co morbid conditions | x | x | x | x | x | MoHW | Technical partners
Strategic Objective 2.14: Enhanced governance and accountability for integrated HIV/STI/VH and TB treatment, care and support
Strengthen governance, accountability and national planning for HIV/STI/VH and TB treatment, support and chronic care | Strengthen coordination for the delivery of HIV/STI/VH and TB treatment, support and chronic care services | 1. Establish National Treatment Technical working group and conduct quarterly meetings for the coordination of treatment, support and chronic care services | x | x | x | x | x | MoHW | NAC/CSO/Technical partners
|  | 2. Conduct quarterly quality assurance/ oversights to public, private and CSO sites delivering HIV/STI/VH and TB treatment. | x | x | x | x | x | MoHW | NAC/CSO/Technical partners
|  | 3. Conduct annual treatment review- identify gaps and opportunities, revise treatment programming and reset treatment targets. | x | x | x | x | x | MoHW | NAC/CSO/Technical partners
|  | 4. Collaborate with Prevention and SI working groups to comprehensively address issues along the prevention and treatment and care continuum including linkage to care | x | x | x | x | x | MoHW | NAC/CSO/Technical partners
Strategic Priority Area 3: Resilient and Sustainable Systems, an Enabling Environment and Human Rights for Equity
Strategic Objective 3.1: Strengthen advocacy for pro health legislations and initiatives to remove legal, institutional and service delivery barriers
Creating an enabling Environment for increased access to services | Advocacy for pro health laws and policies | 1. Conduct ongoing advocacy for the passing of the Equal Opportunities Bill, National Gender Policy and others that are pro health and relevant to HIV/STI/VH and TB | x | x | x | x | x | NAC | MoHW/CSO/technical partners
|  | 2. Sensitise CSO, KPs and other stakeholders on the key legisations that impact access to health | x | x | x | x | x | NAC | MoHW/CSO/technical partners
|  | 3.Build CSO and KP capacity to support advovacy | x | x | x | x | x | NAC | CSO/technical partners
| Strengthen mechanisms for monitoring and reporting and to provide redress for Human Rights Violations | 1. Scale up the Human Rights Observatory for greater government ownership and multi sectoral engagement- CSO, Law enforcement agencies | x | x | x | x | x | NAC | CSO/technical partners
|  | 2. Link the Human Rights Observatory to the Belize Health Information Systems for comprehensive reporting on risk, human rights violation and disease acquisition and transmission | [6 empty] | CSO/technical partners
|  | 3. Develop a network of legal practitioners to support redress actions for Human Rights Violations | x | x | x | x | x | NAC | CSO/technical partners
|  | 4. Develop a network of paralegals who can serve as gate keepers and support the KPs community to report HR violations | x | x | x | x | x | NAC | CSO/technical partners
|  | 5. Conduct rights based legal literacy training to empower Key Populations, PLHIV to understand their rights, understand when these are violated and mechanisms for reporting violations | x | x | x | x | x | NAC | CSO/technical partners
|  | 6. Develop and implement communication strategies to increase awareness among people with HIV/STI/VH and TB focusing on key populations when and how to access the redress mechanism | x | x | x | x | x | NAC | CSO/technical partners
|  | 7. Strenghten multisectoral collaboration including the referral system to address human rights violations, stigma and discrinimation- Ministry of Legal Affairs, Ministry of Housing, Ministry of Labour, Legal Aide clinics, the Polic Forces and others | x | x | x | x | x | NAC | CSO/technical partners
| Removing institutional delivery barriers | 1. Review policies and practices for the health care system geared at removing stigma and discrimination in the health care settings and at community sites | x | x | x | x | x | NAC | CSO/technical partners
|  | 2. Conduct Stigma Index survey to measure stigma and discrimination |  | x |  |  | x | NAC | CSO/technical partners
|  | 3. Implement recommendations to reduce stigma and discrimination |  |  | x | x | x | NAC | CSO/MoHW/Technical partners
| Strenghten the Belize Network of People Living with HIV | 1. Conduct an organisational assessment and develop a capacity building plan to stregnthen the Belize Network of Seropositives | x |  |  |  |  | NAC | Belize Network of Seropositives
|  | 2. Build a network of human rights advocates among PLHIVs to support and refer PLHIVs who face human rights violations including in the health case setting | x | x | x | x | x | NAC | Belize Network of Seropositives
| Removing Service Delivery Barriers | 1. Sensitise Health Care Workersand patients on Patient Bill of Rights | x | x | x | x | x | MoHW
|  | 2. Train public and private sector and CSO service providers on Human Rights and on delivering services in a non-judgmental way, void of any sigma and discrimination and with respect for all. | x | x | x | x | x | NAC | CSO/MoHW/Technical partners
Strategic Objective 3.2: Strengthen capacity and protect human resources to adequately address HIV/STI/VH and TB responses
Strengthening/Addressing Human Resources for Equity | Understanding the HR needs and adapting HR innovations for efficiencies | 1. Conduct HR assessment for the leadership, coordination and management of the HIV/STI/VH and TB Strategic Plan | x |  |  |  |  | MoHW/NAC | technical partners
|  | 2. Implement recommendations to strenghten the coordinaton of the national HIV/STI/VH and TB response | x | x |  |  |  | MoHW/NAC | technical partners
|  | 3. Revisit HR policy to incorporate task shifting and task sharing and the use of lay counsellors for testing fro HIV/STI/VH and TB | x |  |  |  |  | MoHW | technical partners
|  | 4. Conduct assessment of the HIV/STI/VH/TB work force and make recommendations for efficiencies | x |  |  |  |  | MoHW | NAC/CSO/techncial partners
| Protect the health workforce | 1. Develop a comprehensive and tailored occupational and safety health plans for different categories of the health workforce. | x |  |  |  |  | MoHW | Ministry of Labour ( Human Development?)/Technical partners
|  | 2. Strenghten post exposure prophylaxis for HIV for health care workers | x | x | x | x | x | MoHW
|  | 3. Provide adequate supply of tools and equipment necessary for occupational safety and health including PPE, Biohazard equipment and others | x | x | x | x | x | MoHW
Strategic Objective 3.3: Achieve Robust and Effective Supply Chain Management for uninterrupted supplies of quality assured of medicines and commodities.
Supply Chain Management Systems- ensuring supplies of good quality ARVs, STI, TB, VH medicines, diagnostics and supplies | Strengthen Supply Chain Management Systems for HIV/STI/VH and TB medicines, commodities and supplies | 1. Establish a quantification working group to lead quantification process and conduct regular review of stock on hand | x |  |  |  |  | MoHW | Technical partners
|  | 2. Conduct annual morbidity quantification and forecasting | x | x | x | x | x | MoHW | technical partners
|  | 3. Procure all equipment, medicines, consumables, supplies and health products for HIV/ STIs/ VH and TB that are quality assured | x | x | x | x | x | MoHW
|  | 4. Utilise mechanisms such as the PAHO pool procurement and PAHO Strategic Fund | x | x | x | x | x | MoHW | technical partners
|  | 5. Regularly update the list of essential medicines to incorporate new medicines for HIV/STI/ VH and TB | x |  | x |  | x | MoHW | Technical partners
Strategic Priority Area 4: Responding for Sustainability
Strategic Objective 4.1: Estimate resource needs for the HIV/STI/VH and TB response and implement measures to address financial gaps
Develop and cost an investment case for HIV/STI/VH and TB |  | 1. Develop the investment case with technical leadership from UNAIDS and other technical agencies | x |  |  |  |  | NAC | Ministry of Finance/UNAIDS/ Other technical partners
|  | 2. Conduct stakeholder consultation to share approaches and recommendations for smart investments with national stakeholders |  | x |  |  |  | NAC | Ministry of Finance/UNAIDS/ Other technical partners
|  | 3. Implement recommendations of the investment case. Utilise key findings and recommendations of the investment case to advocate with the political leadership including the Minister of Finance for increased domestic allocation of resources |  | x | x | x | x | NAC | Ministry of Finance/UNAIDS/ Other technical partners
|  | 4. Utilise key findings and recommendations of the investment case to guide funding request to the Global Fund and other funding agencies |  | x |  |  |  | NAC | Ministry of Finance/UNAIDS/ Other technical partners
|  | 5. Prepare policy brief for high level policy makers on the recommendations for smart investments and increase in domestic financing |  | x |  |  |  | NAC | Ministry of Finance/UNAIDS/ Other technical partners
Estimate resource needs for the HIV/STI/VH and TB response and implement measures to address financial gaps | Conduct costing of the National HIV/STI/VH and TB Plan 2021-2025 | 1. Develop terms of reference and establish a technical working group to guide the costing of the National HIV/STI/VH and TB Plan 2021-2025 | x |  |  |  |  | NAC | Ministry of Finance, Technical partners
|  | 2. Conduct stakeholder consultation to share the costing plan | x |  |  |  |  | NAC | Ministry of Finance, Technical partners
|  | 3. Conduct advocacy with political leadership including the Minister of Finance to highlight the funding gaps | x | x | x | x | x | NAC | Ministry of Finance, Technical partners
| Identify the resource gap and implement measures to bridge the gap | 1. Develop and implement resource mobilisation plan to bridge the resource gap | x | x | x | x | x | NAC | Ministry of Finance, Technical partners
|  | 2. Prepare and submit funding proposal to the Global Fund in 2021 for three years of funding | x |  |  |  |  | NAC | Ministry of Finance, Technical partners and Cso
| Conduct regular NHA and NASA (every two years?) | 1. Conduct NASA, share findings and recommendations of NASA |  | x |  |  | x | NAC/MoHW | Ministry of Finance, Technical partners and Cso
|  | 2. Implement recommendations of the NASA |  | x | x | x | x | NAC/MoHW | Ministry of Finance, Technical partners and Cso
| Conduct costing and effectiveness analysis of new strategies-PrEP, Essential Package of Services and Combination Prevention Package of Services for HIV/STI/VH and TB | 1. Conduct costing and cost analyses, Share findings and recommendations | x |  |  |  |  | MoHW | NAC/MoF
|  | 2, Implement recommendation of the costing and cost analyses | x | x |  |  |  | MoHW | NAC/MoF
|  | 3. Conduct hands on training and mentoring of local team to conduct spending assessments, costing and costing analysis. | x | x |  |  | x | MoHW | NAC/MoF
Strategic Objective 4.2: Engage the Belize NHI for financial protection and reduce financial risk in expanding scope and scale of services
| Engage the Belize National Health Insurance | 1. Review regulatory frameworks and define mechanisms to include components of the essential package of services for HIV/STI/VH and TB services as part their menu of services for funding | x | x |  |  |  | MoHW/NHI | NAC/MoF
|  | 2. Define with the NHI, elements of the essential package of services that will be included in the NHI menu of services |  | x |  |  |  | MoHW/NHI | NAC/MoF
Strategic Objective 4.3 Secure reduce prices and increase competitiveness for medicines, commodities and supplies for HIV/STI/VH and TB
Secure reduce prices and increase competitiveness for medicines, commodities and supplies for HIV/STI/VH and TB |  | 1. Establish a high level working group with partners, donors, Ministry of Finance and other government agencies to address policies that will to reduce prices and greater competitiveness, understand the dynamics and shifts in supply chain and identify opportunities for reduced prices. | x |  |  |  |  | MoHW | NAC/MoF
Strategic Objective 4.4 Implement Innovative Financing mechanisms particularly to key populations response such as social contracting for CSOs
Develop and implement Innovative Financing mechanisms for sustainability | Develop social contracting mechanism with CSO | 1. Develop Systems to fund CSOs- including the development of an MoU or financing Agreement with CSO for social contracting | x
|  | 2. Conduct capacity building- management capacity, technical implementation and monitoring, reporting and evaluation- for CSO to effectively engage in social contracting | x | x | x | x | x | MoHW/NAC | CSO
|  | 3. Provide funding for social contracting of CSOs | x | x | x | x | x | MoHW/NAC | MoF, CSO
|  | 4. Develop and implement systems for monitoring and oversight of CSO social contracting. Conduct oversight and monitoring visits to CSO. Conduct regular CSO social contracting coordination meetings | x | x | x | x | x | MoHW/NAC | CSO
Strategic Objective 4.5: Strenghten Resource Mobilization
Strenghten resource mobilization |  | 1. Develop, implement and monitor resource mobilization strategy. |  | x |  |  |  | NAC | MoF/MoHW
|  | 2. Build CSO capacity for proposal development and resource mobilisation | x |  | x |  | x | NAC | MoHW